|  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- |
| Task Name | Duration | Start | Finish | Predecessors | Resource Names |
| Citizen health care system | 247 days? | Wed4/1/20 | Sun12/13/20 |  |  |
| 1-planning | 27days? | Wed4/1/20 | Tue4/28/20 |  |  |
| a-System request | 5 days | Wed4/1/20 | Mon4/6/20 |  | Abdo Gamal |
| b- feasibility study | 10 days | Mon4/6/20 | Thu4/16/20 | 3 |  |
| i-Technical feasibility | 5 days | Mon4/6/20 | Sat4/11/20 |  | Adnan Mustafa |
| ii-Economic feasibility | 10 days | Mon4/6/20 | Thu4/16/20 |  | Abdo Gamal |
| iii-Organizational feasibility | 5 days | Mon4/6/20 | Sat4/11/20 | 5SS,6SS | Ali Ahmed |
| c-Time estimation | 4 days | Thu4/16/20 | Mon4/20/20 | 4 | Abdo Gamal |
| d-Work plan | 8 days | Mon4/20/20 | Tue4/28/20 | 8 | Adnan Mustafa/software tools |
| e-staff plan | 6 days | Mon4/20/20 | Mon4/27/20 | 9SS | Omer Agamy /Desktop |
| f-Risks | 2 days | Mon4/20/20 | Wed4/22/20 | 10SS | Ahmed Meky |
| M1 | 1 days? | Wed4/1/20 | Wed4/1/20 |  |  |
| 2-Analysis | 72 days? | Wed4/29/20 | Sun7/1/20 | 2 |  |
| a-Questionnaires | 5 days | Wed4/29/20 | Mon5/4/20 |  | Ali Ahmed |
| b-Joint application Development (JAD) | 1 days | Wed4/29/20 | Wed4/29/20 |  | Adnan Mustafa |
| c-Interview | 2 days | Wed4/29/20 | Thu4/30/20 | 14SS,15SS | Abdo Gamal |
| d-Reports | 5 days | Mon5/4/20 | Sat5/9/20 | 14,15,16 | Ahmed Meky |
| e-Requirements | 7 days | Sat5/9/20 | Sun5/17/20 | 17 | Omer Agamy |
| f-Use case | 15 days | Sun5/17/20 | Mon6/1/20 | 18 | Ahmed Meky |
| g-Use case diagram | 27.25day | Mon6/1/20 | Sun7/1/20 | 19 | Adnan Mustafa |
| M2 | 1 day? | Wed4/29/20 | Wed4/29/20 |  |  |
| 3-Design | 58 days | Mon7/13/20 | Thu9/10/20 | 13 |  |
| a-Creating an architecture design | 13 days | Mon7/13/20 | Sun7/26/20 |  |  |
| i-Developing optional | 10 days | Mon7/13/20 | Wed7/22/20 |  | Abdo Gamal/software tools/hardware tools |
| ii-Requirements | 9 days | Mon7/13/20 | Tue7/21/20 |  | Adnan Mustafa/software tools |
| iii-Developing | 11 days | Mon7/13/20 | Thu7/23/20 |  | Ali Ahmed/hardware tools |
| iv-Performance requirements | 9 days | Mon7/13/20 | Tue7/21/20 |  | Ali Ahmed/software tools |
| iiv-Developing security requirements | 13 days | Mon7/13/20 | Sun7/26/20 | 24SS,25SS,26 | Omer Agamy/software tools |
| b-Design database | 10 days | Sun7/26/20 | Wed8/5/20 | 23 |  |
| i-staging database design | 10 days | Sun7/26/20 | Wed8/5/20 |  | Adnan Mustafa/database tools |
| ii-Suspense database design | 8 days | Sun7/26/20 | Mon8/3/20 | 30SS | Abdo Gamal/database tools |
| c-Application design | 36 days? | Wed8/5/20 | Thu9/10/20 | 29 |  |
| i-User interface design | 10 days | Wed8/5/20 | Sun8/16/20 |  | Ali Ahmed/desktop |
| ii-User authentication | 10 days | Sun8/16/20 | Wed8/26/20 | 33 | Ahmed Meky/hardware tools |
| iii-Call logging | 8 days | Wed8/26/20 | Thu9/3/20 | 34 | Omer Agamy/software tools |
| iv-Search | 7 days | Thu9/3/20 | Thu9/10/20 | 35 | Adnan Mustafa/software tools |
| M3 | 1 days? | Wed8/5/20 | Thu8/6/20 |  |  |
|  |  |  |  |  |  |
|  |  |  |  |  |  |
| 4-Implementation | 90 days? | Thu9/10/20 | Sun12/13/20 | 22 |  |
| a-construct database | 13 days | Thu9/10/20 | Thu9/24/20 |  | Ahmed Meky/database tools |
| b-Write program | 17 days | Thu9/24/20 | Mon10/12/20 | 39 | Abdo Gamal/software tools |
| c-Develop database design | 25 days | Mon10/12/20 | Sat11/7/20 | 40 | Ali Ahmed/hardware tools |
| d-Testing | 20 days | Sat11/7/20 | Sat/11/28/20 | 41 | Adnan Mustafa/software tools |
| e-Installation | 15 days | Sat/11/28/20 | Sun12/13/20 | 42 | Omer Agamy/desktop |
| M4 | 1 day? | Thu9/10/20 | Sat9/12/20 |  |  |